## Slide 1: Distribution management system in pharmaceutical
Supervisor:
Mr. Nguyen Van Sang Team Members:
Truong Vo Thien Vu
Ta Duc Tung
Nguyen Trong Viet

## Slide 2: Presentation outline
1. Project Overview
2. Project Management
3. Software Specification
4. Software Design
5. Testing
6. Project Result
7. Demo

## Slide 3: Project overview
1. Current Situation
2. Ideas
3. Solution

## Slide 4: Idea
Functional
  Manage Order.
  Manage Salesman, Manage Drugstore.
  Manage Schedule, support deliveryman have shortest path.
  Storage Order History, Payment History.
Non-Functional
  Steady Running.
  Easy to Upgrade and Maintenance.

## Slide 5: Current situation
Drugstore want to have quick transaction.
Drugstore want to get Product directly from Distributor easily.
Drugstore want to get public and exactly prices.
Most pharmacy company does not user internet for sell online their product.
Drugstore have to contact with Distributor when they need.
Current system: indico.vn, stada.com.vn

## Slide 6: Solution
Popularity
Rich Class Library
Run on Multi-Devices
Experience
Why choose Website&.NET?

## Slide 7: Project management
Project Model
Project Life Cycle
Organization Structure
Master Schedule
Objectives
Deliverables
Tool & Environment

## Slide 8: Project model
Rational Unified Process Model

## Slide 9: Project Life cycle
Phase 1: Inception
  Study Business Case and Feasibility Study of Project
  Complete Project Management Plan
  Complete draft ERD of System
  Complete draft Screen prototypes
  Complete draft Requirements
  Determine Project Scope

## Slide 10: Project Life cycle
Phase 2: Elaboration
  Complete User Requirement Specification
  Complete Software Requirement Specification
  Complete ERD, final prototypes
  Complete Database model
  Complete System Architecture Design

## Slide 11: Project Life cycle
Phase 3: Construction
  Complete Coding and Unit Test
  Complete User manual
  Complete Function and Regression Test
Phase 4: Transition
  Deploy Website
  Complete all Reports and Documents
  Release Source Code

## Slide 12: Project model
Why choose RUP?
Develop Iteratively
  Support an iterative approach to development that addresses the highest risk items at every stage in the lifecycle, significantly reducing a project’s risk.
  Very important for inexperienced team in controlling issues like us.
Manage Requirement
  Managing requirements during the whole development process ensures Project Team develops the right system with right requirement.
Verify Software Quality
  Testing process is implemented in all the cycles of application development time.
  Reduce risks

## Slide 13: Project Organization structure
Supervisor Mr. SangNV
Project Manager
SRS Analysis Team TungTD
Design Team VuTVT
VuTVT
Develop Team VuTVT
Test Team TungTD
TungTD
VietNT
VietNT

## Slide 14: Project schedule master

## Slide 15: Project schedule master

## Slide 16: Project schedule master

## Slide 17: Project schedule master

## Slide 18: Risk management
ID | Risk Content | Probability | Effect | Solution
# | People Risks |  |  | 
1 | Team member may not follow deadlines. | HIGH | SERIOUS | Find out reasons Depending on circumstances, may set penalty rule.
2 | Team members are sick, cannot complete task under deadline. | HIGH | SERIOUS | Increase project team’s working effort in “peace period”. Allow all team members clear about what others do, so that they can cover the tasks when necessary.
3 | Conflict between team members. | HIGH | SERIOUS | Setup an open-talk environment in project team. “Do not criticize” is set as a rule. Organize team-building more often. In some cases, manager must use his power to make decisions.
4 | New technology is hard to apply for project | HIGH | SERIOUS | List tasks and check continuously. Evaluate quality and progress weekly. Send email to other member or supervisor to ask for help.
5 | Problems in communication breakdown makes changing time, work and delay plan | HIGH | SERIOUS | We need using words more clearly, improve our communication skills Using note and email to confirm information.

## Slide 19: Project object
Metrics | Unit | Committed | Actual | Deviation
Start Date | dd-mm-yyyy | 07-09-2015 | 07-09-2015 | 0 day
End Date | dd-mm-yyyy | 19-12-2015 | 21-12-2015 | 2 days
Duration | Elapsed days | 76 days | 78 days | 2 days
Maximum Team Size | Person | 5 | 3 | 2

## Slide 20: Project deliverables
No | Stage | Deliverable/ Milestone | Delivery Date | Delivery Location
1 | Inception | Deliver Report No.1 | 14/09/2015 | Supervisor
2 | Inception | Project plan | 24/09/2015 | Supervisor
3 | Inception | Deliver Report No.2 | 24/09/2015 | Supervisor
4 | Elaboration | Deliver Report No.3 | 08/10/2015 | Supervisor
5 | Elaboration | Deliver Report No.4 | 26/10/2015 | Supervisor
6 | Construction | Complete Coding | 25/11/2015 | Supervisor
7 | Construction | Deliver Report No.5 | 01/12/2015 | Supervisor
8 | Construction | Deliver Report No.6 | 11/12/2015 | Supervisor
9 | Transition | The last Document and CD source code | 16/12/2015 | FU
10 | Transition | Project completed | 21/12/2015 | FU

## Slide 21: Project Tool and environment

## Slide 22: Communication

## Slide 23: Software Specification
System Business Process Overview
Non Functional Requirement
Functional Requirement

## Slide 24: System Business Process overview

## Slide 25: Functional requirement

## Slide 26: Functional requirement

## Slide 27: Functional requirement

## Slide 28: System overview non functional requirement
Usability
  System supports 100% Vietnamese.
  User Interface must be easy to learn, even at the first time looking at the screen, user may immediately understand the function of each button or icon.
Performance
  Approximate time to start and run: 5-7s.
  Approximate time to process action: <3s.
Reliability
  Mean time between two failure: 10 days.
  Available 95% of time.

## Slide 29: Software Design
Architecture Overview
Screen Design
Sequence Diagram
Database Design
Travelling salesman problem
Nearest neighbor algorithm

## Slide 30: System architecture design

## Slide 31: System database design

## Slide 32: Sequence diagram

## Slide 33: Screen design
No | Object/Control Name | Type | Required | Description
1 | Giỏ hang | Label | Yes | Total amount
2 | Tên thuốc | Textbox | Yes | Input Drugname
3 | Đơn vị | Dropdown List | Yes | Unit
4 | Số lượng | Dropdown List | Yes | Quantity

## Slide 34: Travelling salesman problem
The travelling salesman problem (TSP) asks the following question: Given a list of cities and the distances between each pair of cities, what is the shortest possible route that visits each city exactly once and returns to the origin city?
It is an NP-hard problem in combinatorial optimization, important in operations research and theoretical computer science.

## Slide 35: Nearest neighbor algorithm
These are the steps of the algorithm:
  Start on an arbitrary vertex as current vertex.
  Find out the shortest edge connecting current vertex and an unvisited vertex V.
  Set current vertex to V.
  Mark V as visited.
  If all the vertices in domain are visited, then terminate.
  Go to step 2.
The sequence of the visited vertices is the output of the algorithm.

## Slide 36: Nearest neighbor algorithm(cnt)

## Slide 37: Nearest neighbor algorithm(cnt)
Advantages:
  Easy to implement.
  Executes quickly.
Disadvantages:
  Sometimes miss shorter routes which are easily noticed with human insight
  In the worst case, the algorithm results in a tour that is much longer than the optimal tour.

## Slide 38: Software Testing
Test Model
Test Result
Test Process
Test Case

## Slide 39: Test model

## Slide 40: Test process

## Slide 41: Test environment

## Slide 42: Test Case

## Slide 43: Test result

## Slide 44: Project result
After closing project, we achieve goal software:
  Drugstore can order Drug from Distributor and view their history transaction easily.
  Salesman manage Drugstore easily.
  Staff can manage everything easier.
  Deliveryman can delivery good with shortest path.
  Have more experiences of managing a software project: how to manage plan, time, and risk. These experiences help us a lot in our future work.
  How to communicate with other team members and how to do teamwork efficiently.

## Slide 45: DEMO